## Login_testcases
Project Name | Zero bank | [8 empty] | Version | -
Processor+A:SB7A:M | [9 empty] | OS | Windows
RAM | - | [8 empty] | Browser | -
Module Name | login page
Reviewed By | Vaishali sonanis | [8 empty] | Date Reviewed on: | 2025-08-06
SR. NO. | TYPE OF TESTING | TEST CASES NO. | TEST CASE NAME | OBJECTIVE | PRE-REQUISITE | STEPS TO BE FOLLOWED | TEST DATA | EXPECTED OUTPUT | ACTUAL OUTPUT | PASSED / FAILED | BUG ID NO. | BUG ROOT CAUSE | WORK ITEM ASSOCIATED | MAJOR / MINOR BUG | IF MAJOR THEN TYPE | TESTED ON | TESTED BY | REMARKS
1 | functional testing | TC‑001 | TC_ZB_login_valid | Valid login | login page should be open in default browser | Enter valid username and password | username password | Successfully login and navigate to home page | showing error message "This site can’t provide a secure connection" | Fail
2 | functional testing | TC‑002 | TC_ZB_login_user_invalid | Invalid username | login page should be open in default browser | Enter invalid username + valid password; attempt login. | hgdjdgd, password | Display an error message; remain on login page. | display error message "Login and/or password invalid" | Passed
3 | functional testing | TC‑003 | TC_ZB_login_pass_invalid | Invalid password | login page should be open in default browser | Enter valid username + wrong password; attempt login. | username,hfdkjFKDJ | Display an error message; remain on login page. | display error message "Login and/or password invalid" | Passed
4 | functional testing | TC‑004 | TC_ZB_login_both_invalid | Both fields empty | login page should be open in default browser | Leave both username & password blank; click Login. | keep blank | Display validation messages for required fields. | display error message "Login and/or password invalid" | Passed
5 | functional testing | TC‑005 | TC_ZB_login_both_invalid | Both fields invalid | login page should be open in default browser | add both invalid username and password | hadkjf,gfdgdu 6747476,64343 #@%,$%@^$ | Display validation messages for required fields. | display error message "Login and/or password invalid" | Passed
6 | functional testing | TC‑006 | TC_ZB_login/logout | Session persistence after logout | login page should be open in default browser | Login, then log out and click browser back/reset tab. |  | logout and stay on home page without login | logout and stay on home page without login | Passed
7 | functional testing | TC‑007 | TC_ZB_checkbox | "Keep me signed in" functionality | login page should be open in default browser | Check "Keep me signed in", then close and reopen browser. |  | User stays logged in (if intended), or session is cleared. | yes able click and change selected and unselected | Passed
8 | functional testing | TC‑008 | TC_ZB_login_?Icon | Default credentials present | login page should be open in default browser | Inspect login hint (e.g., via the “?” icon). |  | Hint matches expected default credentials. | yes showing default username and password | Passed
9 | functional testing | TC‑009 | TC_ZB_login_forgotpassword | check forgot password link navigate to next page | login page should be open in default browser | open login page and click on forgot password link |  | forgot password link navigate to next relavant page | navigate to next page | Passed

## defect report
ØDefect identifier | Def_search_001
ØDefect summary | Expected result=When we search a product it should display the searched product only but Actual result=showing not searched products also
ØTest Id | TC‑008 , TC‑009 , TC‑010 , TC‑011
ØTest case name | TC_search_valid_product, TC_search_partial_input, TC_search_invalid_input, TC_search_empty_input
ØModule name | Search
Øreproducible | Enter names to search
Øseverity | Medium
Øpriority | Medium
ØRaised by | Yelisetti Jayanth Srihari(Tester name)
ØAssigned to | (TL name)
ØDate of assignment | 2025-09-04
Østatus | open
ØSnap shots
ØFixed by | Shiva Upadhyay(Developer name
ØDate of fixing=
ØApprovals=manager name | Nisha mandot(Manager name)
Defort Report-2
ØDefect identifier | Def_offers_001
ØDefect summary | Expected result=This module should shows offered products but Actual result=showing empty(No products)
ØTest Id | TC‑020 , TC‑021 , TC‑022 , TC‑023
ØTest case name | Tc_Offers_Page, Tc_Offer_Link_Navigation, Tc_Expired_offers, Tc_add_offers
ØModule name | Offers
Øreproducible | It should show offered products
Øseverity | Medium
Øpriority | Medium
ØRaised by | Yelisetti Jayanth Srihari(Tester name)
ØAssigned to | (TL name)
ØDate of assignment | 2025-09-04
Østatus | open
ØSnap shots
ØFixed by | Shiva Upadhyay(Developer name
ØDate of fixing=
ØApprovals=manager name | Nisha mandot(Manager name)

## testAnalysis_report
Section | Details
Project Name | Zerobank
Module Name | login
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Vaishali sonanis
Date | 2025-08-07
1. Test Summary
Metric | Count
Total Test Cases | 9
Executed Test Cases | 9
Passed Test Cases | 8
Failed Test Cases | 1
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | No
Manual Test Cases | 9
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 8 | 88.88%
Failed | 1 | 11%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 1
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 9 out of 9 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
after login it will show "This site can’t provide a secure connection" but user is able to logedin
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
username and password easily available | Medium | Open | hide username and password
after login it will show this "This site can’t provide a secure connection" so this create confusion | Medium | Open | redirect to Home page
7. Recommendations
hide username and password
redirect to Home page